Continuum Transformation Combined Scope of Work for the remainder of the website development

Purpose

This document combines the immediate Phase 1 launch scope and the follow-on Phase 2 enhancement scope into one developer-facing plan for the Continuum Transformation website, enrollment system, and admin operations experience.

The intent is to prioritize a fast launch for the upcoming May cohort while still defining the broader functionality required for a more complete cohort operations platform.

The proposed total timeline in this document is 4 to 5 weeks across both phases, with final timing to be confirmed by the developer after technical review.

Delivery approach

The project should be delivered in two phases rather than as one full build because Phase 1 needs to support a live cohort start in May and must therefore stay tightly scoped.

Phase 1 focuses on self-pay enrollment, core registration, lightweight admin operations, and essential Mailchimp email and SMS automation.

Phase 2 expands the system into a more complete operational platform with broader lifecycle states, enhanced admin functionality, sponsorship and employer-funding workflows, and deeper reporting.

Proposed timeline

The target schedule below compresses both phases into a 4 to 5 week window, subject to developer confirmation.

| Stage | Focus | Proposed duration | Timing notes |
| --- | --- | --- | --- |
| Stage 0 | Final alignment and setup | 2-3 business days | Confirm scope, finalize fields, approve content, grant Stripe/Mailchimp/admin access |
| Phase 1 | May cohort MVP launch | 2 weeks | Must prioritize self-pay only and essential admin + communications |
| Phase 2 | Operational enhancement build | 2-3 weeks | Begins after Phase 1 core flow is stable in staging or production |

This creates a total estimated timeline of approximately 4 to 5 weeks from kickoff to Phase 2 completion.

Phase 1 scope

Objective

Phase 1 is designed to launch a production-ready, self-pay-only cohort enrollment flow for the May cohort

This phase is focused on minimizing friction for customers and providing the Continuum team with enough operational visibility to manage paid participants successfully.

Phase 1 deliverables

1. Customer-facing experience

The developer will deliver the following Phase 1 customer-facing functionality:

- One cohort detail page with program overview, dates, pricing, seat cap, refund terms, and a clear primary CTA.

- One Stripe Checkout flow for a single one-time USD self-pay option

- One payment success page with next-step instructions.

- One payment failure page with retry path.

- One post-payment registration form for participant details and communications preferences.

2. Registration and participant data capture

The registration form should capture at minimum:

- Name (required)

- Email (required)

- Phone number (required)

- Company (required)

- Role/title

- Cohort identifier (required – this is a dropdown list)

- Intake questions

- Email consent

- SMS consent for reminders where applicable.

3. Admin functionality

The Phase 1 admin panel should support the following minimum operational requirements:

- Secure admin login.

- A simple dashboard showing paid users and registration completion status.

- Participant table including name, email, phone, cohort, payment status, and registration status.

- Basic search and filter by cohort and status.

- CSV export of participant records.

- Manual status update capability for operational fixes.

- One editable cohort configuration record with cohort name, dates, seat limit, price, and open/closed toggle.

4. Stripe integration

Phase 1 Stripe scope includes:

- Secure one-time payment setup.

- Successful and failed transaction handling.

- Minimal payment data storage in the application database.

- Webhook handling for payment success and payment status updates

5. Mailchimp integration

Mailchimp should be used as the communications hub in Phase 1 because it can support a single audience model, lifecycle tags, email journeys, and SMS for properly consented users.

Required Mailchimp implementation for Phase 1:

- One master audience.

- Tags at minimum for cohort-paid-[cohort-name] and cohort-enrolled-[cohort-name].

- Merge fields for cohort, start date, payment status, registration status, and phone.

- Sync after successful payment.

- Sync after registration completion

6. Email and SMS automation

Required Phase 1 communications flows:

- Payment confirmation and next-step email after successful payment.

- Registration completion reminder for paid participants who have not completed registration.

- Pre-cohort reminder email before the start date.

- One reminder SMS to enrolled, properly opted-in participants approximately 24 hours before the first session.

Phase 1 exclusions

The following items are explicitly out of scope for Phase 1:

- Employer-funded flow.

- Sponsorship workflow.

- Installment plans or subscription payments.

- Multi-currency payments.

- Role-based admin permissions.

- Advanced analytics and reporting dashboards beyond simple counts and CSV export.

Phase 1 timeline

| Week | Focus | Deliverable |
| --- | --- | --- |
| Week 1 | Finalize Phase 1 requirements, fields, payment flow, registration fields, and basic admin structure | Approved MVP scope, configured data model, Stripe and Mailchimp setup started |
| Week 2 | Build and test full self-pay flow, registration flow, admin list view, and basic Mailchimp automations | Staging-ready Phase 1 system for end-to-end testing |

A short QA and deployment window should follow immediately at the end of Week 2 or beginning of Week 3 depending on the developer's process.

Phase 2 scope

Objective

Phase 2 expands the Phase 1 MVP into a fuller enrollment operations system and improves the employee experience for the Continuum team.

This phase adds the broader scope already identified in the revised estimate, especially around lifecycle management, reporting, and more advanced admin and funding workflows

Phase 2 deliverables

1. Expanded customer experience

The developer will add or refine:

- Distinct paths for employer-funded, sponsorship inquiry, and waitlist users.

- Additional user flow states such as registration incomplete, waitlisted, and alternate enrollment paths.

- Additional cohort pages or reusable cohort page structure if more than one cohort is being managed.

2. Expanded admin experience

Phase 2 admin enhancements should include:

- Expanded dashboard metrics including total leads, completed enrollments, incomplete registrations, cohort fill rate, failed payments, refunds, and communications exceptions.

- More robust filtering by status, payment state, cohort, and consent state.

- Detailed enrollment record view with timeline/history of payment, registration, communication, and notes.

- Additional admin actions such as resend confirmation, resend registration link, refund support, transfer support, and internal notes.

- Expanded cohort management controls including draft/open/full/closed/archive status and editable pricing or date fields where approved.

3. Lifecycle states and data model expansion

Phase 2 should formalize the broader lifecycle status model recommended in the revised estimate.

Recommended statuses include:

- Lead

- Checkout started

- Payment failed

- Paid

- Registration incomplete

- Enrolled

- Waitlisted

- Employer funding pending

- Sponsorship pending

- Refunded

- Transferred

- Cohort completed

4. Sponsorship and employer-funding workflows

If approved for Phase 2, the developer should build:

- Sponsorship application workflow.

- Employer-funded intake and status management.

- Admin review queue and follow-up notes.

- Employer contact and payment/invoice tracking if required

5. Backend and integration enhancements

Phase 2 backend expansion should include:

- Additional APIs for broader lifecycle and funding flows.

- Expanded webhook and retry/error handling.

- Logging and alerting for failed Mailchimp sync events.

- More complete communication event logging.

6. Reporting and analytics

Phase 2 reporting should include:

- Lead-to-paid conversion.

- Paid-to-registration-complete conversion.

- UTM/source attribution.

- Cohort fill rate and seat utilization.

- Failed payment rate.

- Refund volume.

- Mailchimp email engagement reporting at a basic operational level.

- SMS eligibility and opt-in reporting where applicable.

Phase 2 timeline

| Week | Focus | Deliverable |
| --- | --- | --- |
| Week 3 | Expand admin views, lifecycle statuses, additional cohort workflows, and data model | Enhanced admin and operational logic available in staging |
| Week 4 | Add reporting, expanded communications handling, exception paths, and workflow polish | Phase 2 feature-complete staging build |
| Week 5 (if needed) | QA, bug fixes, UAT, and production stabilization | Final production rollout and handoff |

Week 5 should be treated as a buffer or stabilization week if the developer confirms it is needed.

Combined deliverable summary

| Phase | Primary outcome | Recommended completion target |
| --- | --- | --- |
| Phase 1 | May cohort self-pay launch MVP | End of Week 2 |
| Phase 2 | Broader operations and admin enhancement layer | End of Week 4 or Week 5 |

Assumptions

This combined scope and timing assumes the following:

- Final content, pricing, and cohort details are provided promptly.

- The developer receives timely access to Stripe, Mailchimp, hosting, and admin environments.

- Design decisions for the Phase 1 flow are finalized quickly enough to avoid rework.

- Complex employer-funding or sponsorship invoicing requirements are either simplified or confirmed in detail before Phase 2 begins.

- Continuum and the developer can review deliverables quickly during the sprint window.

Open decisions for developer confirmation

The developer should review and confirm the following before the project schedule is finalized:

- Whether the full combined scope can realistically be completed in 4 to 5 weeks.

- Whether any Phase 2 items need to be deferred beyond Week 5.

- Whether role-based access should remain deferred.

- Whether employer-funded and sponsorship flows are simple enough for inclusion in Phase 2 within this timeline.

- Whether Mailchimp SMS setup timing is dependent on compliance approval timing

- Whether QA and production deployment require a dedicated stabilization window

Recommendation

The developer should use this document as the working plan for sequencing the build, with the understanding that Phase 1 is the non-negotiable launch path and Phase 2 is the enhancement layer to be confirmed against actual development capacity.

The 4 to 5 week timeline is reasonable as a planning target for discussion, but the developer should validate technical feasibility and identify any scope items that should move out of the initial timeline.